## Document Register
Master Document Register
Document Number | Document Title | Project Name | Client Name | Discipline | Revision No. | Submission Date | Approval Date | Status | Responsible Engineer | Remarks | Aging (Days)
PRJ01-CIV-0001 | Foundation Drawing | Metro Project | ABC Ltd | Civil | Rev-00 | 2026-01-01 | 2026-01-04 | Approved | Ahmed Khan | Approved | 221
PRJ02-MEC-0002 | HVAC Layout | Airport Project | XYZ Ltd | Mechanical | Rev-01 | 2026-01-03 |  | Submitted | Ali Raza | Pending | 219
PRJ03-ELE-0003 | Cable Schedule | Hospital Project | GHI Ltd | Electrical | Rev-02 | 2026-01-05 |  | Under Review | John Mathew | Review | 217
PRJ04-ELV-0004 | CCTV Layout | Refinery Upgrade | OilCorp | ELV | Rev-03 | 2026-01-07 |  | Draft | Salman Ali | Draft | 215
PRJ05-HSE-0005 | Risk Assessment | IT Park | PQR Ltd | HSE | Rev-00 | 2026-01-09 |  | Rejected | Imran Ahmed | Resubmit | 213
PRJ06-QA/-0006 | ITP Document | Data Center | NABCO | QA/QC | Rev-01 | 2026-01-11 | 2026-01-14 | Approved | Hassan Khan | Approved | 211
PRJ07-CIV-0007 | Foundation Drawing | Mall Project | Delta EPC | Civil | Rev-02 | 2026-01-13 |  | Submitted | Ahmed Khan | Pending | 209
PRJ08-MEC-0008 | HVAC Layout | Bridge Project | Prime Infra | Mechanical | Rev-03 | 2026-01-15 |  | Under Review | Ali Raza | Review | 207
PRJ09-ELE-0009 | Cable Schedule | Residential Tower | SkyBuild | Electrical | Rev-00 | 2026-01-17 |  | Draft | John Mathew | Draft | 205
PRJ10-ELV-0010 | CCTV Layout | Industrial Plant | Vision Tech | ELV | Rev-01 | 2026-01-19 |  | Rejected | Salman Ali | Resubmit | 203
PRJ01-HSE-0011 | Risk Assessment | Metro Project | ABC Ltd | HSE | Rev-02 | 2026-01-21 | 2026-01-24 | Approved | Imran Ahmed | Approved | 201
PRJ02-QA/-0012 | ITP Document | Airport Project | XYZ Ltd | QA/QC | Rev-03 | 2026-01-23 |  | Submitted | Hassan Khan | Pending | 199
PRJ03-CIV-0013 | Foundation Drawing | Hospital Project | GHI Ltd | Civil | Rev-00 | 2026-01-25 |  | Under Review | Ahmed Khan | Review | 197
PRJ04-MEC-0014 | HVAC Layout | Refinery Upgrade | OilCorp | Mechanical | Rev-01 | 2026-01-27 |  | Draft | Ali Raza | Draft | 195
PRJ05-ELE-0015 | Cable Schedule | IT Park | PQR Ltd | Electrical | Rev-02 | 2026-01-29 |  | Rejected | John Mathew | Resubmit | 193
PRJ06-ELV-0016 | CCTV Layout | Data Center | NABCO | ELV | Rev-03 | 2026-01-31 | 2026-02-03 | Approved | Salman Ali | Approved | 191
PRJ07-HSE-0017 | Risk Assessment | Mall Project | Delta EPC | HSE | Rev-00 | 2026-02-02 |  | Submitted | Imran Ahmed | Pending | 189
PRJ08-QA/-0018 | ITP Document | Bridge Project | Prime Infra | QA/QC | Rev-01 | 2026-02-04 |  | Under Review | Hassan Khan | Review | 187
PRJ09-CIV-0019 | Foundation Drawing | Residential Tower | SkyBuild | Civil | Rev-02 | 2026-02-06 |  | Draft | Ahmed Khan | Draft | 185
PRJ10-MEC-0020 | HVAC Layout | Industrial Plant | Vision Tech | Mechanical | Rev-03 | 2026-02-08 |  | Rejected | Ali Raza | Resubmit | 183
PRJ01-ELE-0021 | Cable Schedule | Metro Project | ABC Ltd | Electrical | Rev-00 | 2026-02-10 | 2026-02-13 | Approved | John Mathew | Approved | 181
PRJ02-ELV-0022 | CCTV Layout | Airport Project | XYZ Ltd | ELV | Rev-01 | 2026-02-12 |  | Submitted | Salman Ali | Pending | 179
PRJ03-HSE-0023 | Risk Assessment | Hospital Project | GHI Ltd | HSE | Rev-02 | 2026-02-14 |  | Under Review | Imran Ahmed | Review | 177
PRJ04-QA/-0024 | ITP Document | Refinery Upgrade | OilCorp | QA/QC | Rev-03 | 2026-02-16 |  | Draft | Hassan Khan | Draft | 175
PRJ05-CIV-0025 | Foundation Drawing | IT Park | PQR Ltd | Civil | Rev-00 | 2026-02-18 |  | Rejected | Ahmed Khan | Resubmit | 173
PRJ06-MEC-0026 | HVAC Layout | Data Center | NABCO | Mechanical | Rev-01 | 2026-02-20 | 2026-02-23 | Approved | Ali Raza | Approved | 171
PRJ07-ELE-0027 | Cable Schedule | Mall Project | Delta EPC | Electrical | Rev-02 | 2026-02-22 |  | Submitted | John Mathew | Pending | 169
PRJ08-ELV-0028 | CCTV Layout | Bridge Project | Prime Infra | ELV | Rev-03 | 2026-02-24 |  | Under Review | Salman Ali | Review | 167
PRJ09-HSE-0029 | Risk Assessment | Residential Tower | SkyBuild | HSE | Rev-00 | 2026-02-26 |  | Draft | Imran Ahmed | Draft | 165
PRJ10-QA/-0030 | ITP Document | Industrial Plant | Vision Tech | QA/QC | Rev-01 | 2026-02-28 |  | Rejected | Hassan Khan | Resubmit | 163
PRJ01-CIV-0031 | Foundation Drawing | Metro Project | ABC Ltd | Civil | Rev-02 | 2026-03-02 | 2026-03-05 | Approved | Ahmed Khan | Approved | 161
PRJ02-MEC-0032 | HVAC Layout | Airport Project | XYZ Ltd | Mechanical | Rev-03 | 2026-03-04 |  | Submitted | Ali Raza | Pending | 159
PRJ03-ELE-0033 | Cable Schedule | Hospital Project | GHI Ltd | Electrical | Rev-00 | 2026-03-06 |  | Under Review | John Mathew | Review | 157
PRJ04-ELV-0034 | CCTV Layout | Refinery Upgrade | OilCorp | ELV | Rev-01 | 2026-03-08 |  | Draft | Salman Ali | Draft | 155
PRJ05-HSE-0035 | Risk Assessment | IT Park | PQR Ltd | HSE | Rev-02 | 2026-03-10 |  | Rejected | Imran Ahmed | Resubmit | 153
PRJ06-QA/-0036 | ITP Document | Data Center | NABCO | QA/QC | Rev-03 | 2026-03-12 | 2026-03-15 | Approved | Hassan Khan | Approved | 151
PRJ07-CIV-0037 | Foundation Drawing | Mall Project | Delta EPC | Civil | Rev-00 | 2026-03-14 |  | Submitted | Ahmed Khan | Pending | 149
PRJ08-MEC-0038 | HVAC Layout | Bridge Project | Prime Infra | Mechanical | Rev-01 | 2026-03-16 |  | Under Review | Ali Raza | Review | 147
PRJ09-ELE-0039 | Cable Schedule | Residential Tower | SkyBuild | Electrical | Rev-02 | 2026-03-18 |  | Draft | John Mathew | Draft | 145
PRJ10-ELV-0040 | CCTV Layout | Industrial Plant | Vision Tech | ELV | Rev-03 | 2026-03-20 |  | Rejected | Salman Ali | Resubmit | 143
PRJ01-HSE-0041 | Risk Assessment | Metro Project | ABC Ltd | HSE | Rev-00 | 2026-03-22 | 2026-03-25 | Approved | Imran Ahmed | Approved | 141
PRJ02-QA/-0042 | ITP Document | Airport Project | XYZ Ltd | QA/QC | Rev-01 | 2026-03-24 |  | Submitted | Hassan Khan | Pending | 139
PRJ03-CIV-0043 | Foundation Drawing | Hospital Project | GHI Ltd | Civil | Rev-02 | 2026-03-26 |  | Under Review | Ahmed Khan | Review | 137
PRJ04-MEC-0044 | HVAC Layout | Refinery Upgrade | OilCorp | Mechanical | Rev-03 | 2026-03-28 |  | Draft | Ali Raza | Draft | 135
PRJ05-ELE-0045 | Cable Schedule | IT Park | PQR Ltd | Electrical | Rev-00 | 2026-03-30 |  | Rejected | John Mathew | Resubmit | 133
PRJ06-ELV-0046 | CCTV Layout | Data Center | NABCO | ELV | Rev-01 | 2026-04-01 | 2026-04-04 | Approved | Salman Ali | Approved | 131
PRJ07-HSE-0047 | Risk Assessment | Mall Project | Delta EPC | HSE | Rev-02 | 2026-04-03 |  | Submitted | Imran Ahmed | Pending | 129
PRJ08-QA/-0048 | ITP Document | Bridge Project | Prime Infra | QA/QC | Rev-03 | 2026-04-05 |  | Under Review | Hassan Khan | Review | 127
PRJ09-CIV-0049 | Foundation Drawing | Residential Tower | SkyBuild | Civil | Rev-00 | 2026-04-07 |  | Draft | Ahmed Khan | Draft | 125
PRJ10-MEC-0050 | HVAC Layout | Industrial Plant | Vision Tech | Mechanical | Rev-01 | 2026-04-09 |  | Rejected | Ali Raza | Resubmit | 123
PRJ01-ELE-0051 | Cable Schedule | Metro Project | ABC Ltd | Electrical | Rev-02 | 2026-04-11 | 2026-04-14 | Approved | John Mathew | Approved | 121
PRJ02-ELV-0052 | CCTV Layout | Airport Project | XYZ Ltd | ELV | Rev-03 | 2026-04-13 |  | Submitted | Salman Ali | Pending | 119
PRJ03-HSE-0053 | Risk Assessment | Hospital Project | GHI Ltd | HSE | Rev-00 | 2026-04-15 |  | Under Review | Imran Ahmed | Review | 117
PRJ04-QA/-0054 | ITP Document | Refinery Upgrade | OilCorp | QA/QC | Rev-01 | 2026-04-17 |  | Draft | Hassan Khan | Draft | 115
PRJ05-CIV-0055 | Foundation Drawing | IT Park | PQR Ltd | Civil | Rev-02 | 2026-04-19 |  | Rejected | Ahmed Khan | Resubmit | 113
PRJ06-MEC-0056 | HVAC Layout | Data Center | NABCO | Mechanical | Rev-03 | 2026-04-21 | 2026-04-24 | Approved | Ali Raza | Approved | 111
PRJ07-ELE-0057 | Cable Schedule | Mall Project | Delta EPC | Electrical | Rev-00 | 2026-04-23 |  | Submitted | John Mathew | Pending | 109
PRJ08-ELV-0058 | CCTV Layout | Bridge Project | Prime Infra | ELV | Rev-01 | 2026-04-25 |  | Under Review | Salman Ali | Review | 107
PRJ09-HSE-0059 | Risk Assessment | Residential Tower | SkyBuild | HSE | Rev-02 | 2026-04-27 |  | Draft | Imran Ahmed | Draft | 105
PRJ10-QA/-0060 | ITP Document | Industrial Plant | Vision Tech | QA/QC | Rev-03 | 2026-04-29 |  | Rejected | Hassan Khan | Resubmit | 103
PRJ01-CIV-0061 | Foundation Drawing | Metro Project | ABC Ltd | Civil | Rev-00 | 2026-05-01 | 2026-05-04 | Approved | Ahmed Khan | Approved | 101
PRJ02-MEC-0062 | HVAC Layout | Airport Project | XYZ Ltd | Mechanical | Rev-01 | 2026-05-03 |  | Submitted | Ali Raza | Pending | 99
PRJ03-ELE-0063 | Cable Schedule | Hospital Project | GHI Ltd | Electrical | Rev-02 | 2026-05-05 |  | Under Review | John Mathew | Review | 97
PRJ04-ELV-0064 | CCTV Layout | Refinery Upgrade | OilCorp | ELV | Rev-03 | 2026-05-07 |  | Draft | Salman Ali | Draft | 95
PRJ05-HSE-0065 | Risk Assessment | IT Park | PQR Ltd | HSE | Rev-00 | 2026-05-09 |  | Rejected | Imran Ahmed | Resubmit | 93
PRJ06-QA/-0066 | ITP Document | Data Center | NABCO | QA/QC | Rev-01 | 2026-05-11 | 2026-05-14 | Approved | Hassan Khan | Approved | 91
PRJ07-CIV-0067 | Foundation Drawing | Mall Project | Delta EPC | Civil | Rev-02 | 2026-05-13 |  | Submitted | Ahmed Khan | Pending | 89
PRJ08-MEC-0068 | HVAC Layout | Bridge Project | Prime Infra | Mechanical | Rev-03 | 2026-05-15 |  | Under Review | Ali Raza | Review | 87
PRJ09-ELE-0069 | Cable Schedule | Residential Tower | SkyBuild | Electrical | Rev-00 | 2026-05-17 |  | Draft | John Mathew | Draft | 85
PRJ10-ELV-0070 | CCTV Layout | Industrial Plant | Vision Tech | ELV | Rev-01 | 2026-05-19 |  | Rejected | Salman Ali | Resubmit | 83
PRJ01-HSE-0071 | Risk Assessment | Metro Project | ABC Ltd | HSE | Rev-02 | 2026-05-21 | 2026-05-24 | Approved | Imran Ahmed | Approved | 81
PRJ02-QA/-0072 | ITP Document | Airport Project | XYZ Ltd | QA/QC | Rev-03 | 2026-05-23 |  | Submitted | Hassan Khan | Pending | 79
PRJ03-CIV-0073 | Foundation Drawing | Hospital Project | GHI Ltd | Civil | Rev-00 | 2026-05-25 |  | Under Review | Ahmed Khan | Review | 77
PRJ04-MEC-0074 | HVAC Layout | Refinery Upgrade | OilCorp | Mechanical | Rev-01 | 2026-05-27 |  | Draft | Ali Raza | Draft | 75
PRJ05-ELE-0075 | Cable Schedule | IT Park | PQR Ltd | Electrical | Rev-02 | 2026-05-29 |  | Rejected | John Mathew | Resubmit | 73
PRJ06-ELV-0076 | CCTV Layout | Data Center | NABCO | ELV | Rev-03 | 2026-05-31 | 2026-06-03 | Approved | Salman Ali | Approved | 71
PRJ07-HSE-0077 | Risk Assessment | Mall Project | Delta EPC | HSE | Rev-00 | 2026-06-02 |  | Submitted | Imran Ahmed | Pending | 69
PRJ08-QA/-0078 | ITP Document | Bridge Project | Prime Infra | QA/QC | Rev-01 | 2026-06-04 |  | Under Review | Hassan Khan | Review | 67
PRJ09-CIV-0079 | Foundation Drawing | Residential Tower | SkyBuild | Civil | Rev-02 | 2026-06-06 |  | Draft | Ahmed Khan | Draft | 65
PRJ10-MEC-0080 | HVAC Layout | Industrial Plant | Vision Tech | Mechanical | Rev-03 | 2026-06-08 |  | Rejected | Ali Raza | Resubmit | 63
PRJ01-ELE-0081 | Cable Schedule | Metro Project | ABC Ltd | Electrical | Rev-00 | 2026-06-10 | 2026-06-13 | Approved | John Mathew | Approved | 61
PRJ02-ELV-0082 | CCTV Layout | Airport Project | XYZ Ltd | ELV | Rev-01 | 2026-06-12 |  | Submitted | Salman Ali | Pending | 59
PRJ03-HSE-0083 | Risk Assessment | Hospital Project | GHI Ltd | HSE | Rev-02 | 2026-06-14 |  | Under Review | Imran Ahmed | Review | 57
PRJ04-QA/-0084 | ITP Document | Refinery Upgrade | OilCorp | QA/QC | Rev-03 | 2026-06-16 |  | Draft | Hassan Khan | Draft | 55
PRJ05-CIV-0085 | Foundation Drawing | IT Park | PQR Ltd | Civil | Rev-00 | 2026-06-18 |  | Rejected | Ahmed Khan | Resubmit | 53
PRJ06-MEC-0086 | HVAC Layout | Data Center | NABCO | Mechanical | Rev-01 | 2026-06-20 | 2026-06-23 | Approved | Ali Raza | Approved | 51
PRJ07-ELE-0087 | Cable Schedule | Mall Project | Delta EPC | Electrical | Rev-02 | 2026-06-22 |  | Submitted | John Mathew | Pending | 49
PRJ08-ELV-0088 | CCTV Layout | Bridge Project | Prime Infra | ELV | Rev-03 | 2026-06-24 |  | Under Review | Salman Ali | Review | 47
PRJ09-HSE-0089 | Risk Assessment | Residential Tower | SkyBuild | HSE | Rev-00 | 2026-06-26 |  | Draft | Imran Ahmed | Draft | 45
PRJ10-QA/-0090 | ITP Document | Industrial Plant | Vision Tech | QA/QC | Rev-01 | 2026-06-28 |  | Rejected | Hassan Khan | Resubmit | 43
PRJ01-CIV-0091 | Foundation Drawing | Metro Project | ABC Ltd | Civil | Rev-02 | 2026-06-30 | 2026-07-03 | Approved | Ahmed Khan | Approved | 41
PRJ02-MEC-0092 | HVAC Layout | Airport Project | XYZ Ltd | Mechanical | Rev-03 | 2026-07-02 |  | Submitted | Ali Raza | Pending | 39
PRJ03-ELE-0093 | Cable Schedule | Hospital Project | GHI Ltd | Electrical | Rev-00 | 2026-07-04 |  | Under Review | John Mathew | Review | 37
PRJ04-ELV-0094 | CCTV Layout | Refinery Upgrade | OilCorp | ELV | Rev-01 | 2026-07-06 |  | Draft | Salman Ali | Draft | 35
PRJ05-HSE-0095 | Risk Assessment | IT Park | PQR Ltd | HSE | Rev-02 | 2026-07-08 |  | Rejected | Imran Ahmed | Resubmit | 33
PRJ06-QA/-0096 | ITP Document | Data Center | NABCO | QA/QC | Rev-03 | 2026-07-10 | 2026-07-13 | Approved | Hassan Khan | Approved | 31
PRJ07-CIV-0097 | Foundation Drawing | Mall Project | Delta EPC | Civil | Rev-00 | 2026-07-12 |  | Submitted | Ahmed Khan | Pending | 29
PRJ08-MEC-0098 | HVAC Layout | Bridge Project | Prime Infra | Mechanical | Rev-01 | 2026-07-14 |  | Under Review | Ali Raza | Review | 27
PRJ09-ELE-0099 | Cable Schedule | Residential Tower | SkyBuild | Electrical | Rev-02 | 2026-07-16 |  | Draft | John Mathew | Draft | 25
PRJ10-ELV-0100 | CCTV Layout | Industrial Plant | Vision Tech | ELV | Rev-03 | 2026-07-18 |  | Rejected | Salman Ali | Resubmit | 23
Formulas:
Aging (Days) = IF([Submission Date]="","",TODAY()-[Submission Date])

## Data-detail
Project Name | Client Name | Discipline | Responsible Engineer
Metro Project | ABC Ltd | Civil | Ahmed Khan
Airport Project | XYZ Ltd | Mechanical | Ali Raza
Hospital Project | GHI Ltd | Electrical | John Mathew
IT Park | PQR Ltd | ELV | Salman Ali
Mall Project | DEF Ltd | HSE | Imran Ahmed
Refinery | OilCorp | QA/QC | Hassan Khan
Bridge Project | LMN Ltd | Civil | Ahmed Khan

## KPI Matrix
KPI | Formula | Target
Total Documents | 101 | 200
Approved | 20 | ≥90%
Submitted | 20 | -
Under Review | 20 | -
Rejected | 20 | <5%
Overdue | 76 | <5%
On-Time Submission % | 3.9604 | ≥95%
Approval Success Rate | 19.802 | ≥90%
Document Accuracy % | 100 | ≥99%

## KRA
KRA | Objective | Responsibilities | Measurement
Document Control | Maintain project documents | Register, revise, archive | 99% Accuracy
Submission Management | Timely submissions | Submit & track approvals | ≥95% On-Time
Client Coordination | Client communication | Follow up comments | ≥90% Approval
Reporting & Dashboard | Prepare reports | Excel & Power BI updates | 100% Reports
QA/QC Documentation | Maintain QA records | ITP, Method Statement | Zero Missing Docs
Records Management | Archive records | Store & retrieve documents | 100% Retrieval